## Sheet1
St Mark Community Fridge Pantry Project
| Project Work | Contractor | Contact Information | Bid Amount | Accepted (X) | Invoice Amount Paid | Notes |  | Secondary Sidewalk Work
| Outside Door | Elite Glass | rbucklin@eliteglassandmetal.com | 5980 | X | 5405.8 | 48" entry door | tax not included
| Inside Door | Elite Glass | Ryan Bucklin | 850 | X | 850 | Steel clad panel install | tax not included
| Hadicap Door Opener | Walsh Door | Stew Bevis | 3982.59 | X | 3982.59 | Install 2/21
| Electrical Work | Waldinger Mechanical | Chris Howe/Tony Stelpflug | 1210 | X | 1210 | Completed
| HVAC | Hansman Mechanical | Dave Hansman | 5750 | X | 5650 | Completed
| Concrete | Rams Construction/EBN | Spenser Zeger/Juan Perez | 3550 |  |  |  |  | $3240.00 ramp sidewalk
| Roofing | ForSure Roofing | Colton Fors | 631.76 | X | 631.76 | Completed
| Interior Door Lock | Strauss Security | Justin | 2268.95 | X |  | Ordered 1-24 | 4 weeks lead
| Shelving | Uline | Uline.com | 2191.12 | X | 2191.12 | Arriving 2/15
| Refrigerator | Hockenbergs | JP Paul | 5288.88 | X | 5281.88 | Arriving 3/6 | 1-2 Weeks
| Freezer | Hockenbergs | TriMark Fridge/Atosa Freezer |  |  |  |  | $100 Delivery Charge
|  | Hockenbergs | Delivery Fee |  |  |  |  | $170 Freight Fee
Fixtures | Trash Can | Uline
| Rugs | Uline
| Misc Room supplies | Amazon | Therm cover and Exit sign |  |  | 66.17
|  |  | Total | 31703.3 | Total | 25269.32
Total Dollars Received | 33213.91
Total Paid | -25269.32
Remaining Available | 7944.59