**Next meeting on Mon. 21. Nov. 22**

**Topics of Meeting:**

**1.** Do you want this to be an official CSPE action project for your class or not?

**2**. I will show you a visual of what I perceive the finished mural to look like. This will give us a sensible idea of how many students can be involved in the actual making process.

**3.** Brainstorm a list of sub committees students can be a part of. ie Communications com. / Design com. / Social Media com. Etc

I want parents involved – they can make a couple of panels. Sharon Murray will help us here. I can do an afternoon session with a group of parents and some students can help.

**4.** I will give you a time plan for the project and introduce you to the Artist working with us - Nathalie El Baba.

**Over all Plan**: To design and create a large scale Mosaic Mural in the School which will incorporate the 3 strands of CSPE. The project will be an opportunity for teachers and students to learn about cross curricular teaching and learning and how we can approach various themes in a more creative manner.

**Nov - Jan**: In class: brainstorming of 3 CSPE Strands –

* Rights & Responsibilities
* Global Citizenship
* Exploring Democracy.

Students will

Explore theme (strand) and create visual brainstorms.

Collect images using – imagination – internet - magazines etc.

Draw final designs.

Count the number of designs created - be clear how many wooden panels are required and what sizes are needed. Chat to Mark about this too.

Order circular wooden panels from WW teacher. Maybe some students can do the cutting???

Transfer designs onto wooden panels.

**Jan (or sooner)** – Order Material (Nathalie ElBaba will guide us here etc). Mosaic

tiles/adhesive/grout, tile cutters...

**Feb -** Nathalie El Baba school visit, giving a workshop to a cohort of students and teachers. These student will then help and instruct classmates.

**March 31-** Try to have individual and group mosaics completed before Easter Break so that we can begin mounting and assembling after the Easter break.

**Mid April – end May:** Assemble and mount mosaic.

Organise an unveiling ceremony. Invite parents/local community groups etc