Woodcraft Rangers – Music Will – Project Plan

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| GOAL | | | | | | | | | |
| Woodcraft Rangers will provide students with the opportunity to express themselves and positively impact their community through music | | | | | | | | | |
| Action Step  Description | | Party Responsible | Date | | Resources Required | Desired Outcome | | Notes |
| Register with Music Will | | Austin Lara,  Gerardo Perez | 11/18/22 | | Laptop | Sign up for music will workshop | |  |
| Complete training | | Gerardo Perez | 11/27/22 | | Transportation,  Computer | Gerardo Perez will complete Modern Band 101 workshop | | In-person or online |
| Complete principal consent form | | Austin Lara,  Jessica Rendon,  Jumana Rose | 11/30/22 | | Consent form | Ms. Rendon will complete Music Will consent form | | Permission to offer band program |
| Register class | | Austin Lara,  Gerardo Perez,  Kid Leaders | 12/2/22 | | Laptop | Complete registration and music will survey | | Use data to provide instruments |
| Make music | | Gerardo Perez, Kid Leaders,  students | 12/5/22 – 12/13/22 | | Instruments | Students practice for performance | | Kid Leaders will help facilitate |
| Music performance | | Austin Lara,  Gerardo Perez,  School Admin,  Students | 12/14/22 | | Instruments | Students perform for Toy Drive event | | Woodcraft Rangers – Music will group will host event |
| Budget | | | | | | | | |
| Total budget | Instrument storage | | | Music equipment | | | Event budget | |
| $1000 | $500 | | | $300 | | | $200 | |