Woodcraft Rangers – Music Will – Project Plan

|  |
| --- |
| GOAL |
|  Woodcraft Rangers will provide students with the opportunity to express themselves and positively impact their community through music |
| Action StepDescription | Party Responsible | Date | Resources Required | Desired Outcome | Notes |
| Register with Music Will | Austin Lara,Gerardo Perez | 11/18/22 | Laptop | Sign up for music will workshop |  |
| Complete training | Gerardo Perez | 11/27/22 | Transportation,Computer | Gerardo Perez will complete Modern Band 101 workshop | In-person or online |
| Complete principal consent form | Austin Lara,Jessica Rendon,Jumana Rose | 11/30/22 | Consent form | Ms. Rendon will complete Music Will consent form  | Permission to offer band program |
| Register class | Austin Lara,Gerardo Perez,Kid Leaders | 12/2/22 | Laptop | Complete registration and music will survey | Use data to provide instruments |
| Make music | Gerardo Perez, Kid Leaders,students | 12/5/22 – 12/13/22 | Instruments | Students practice for performance | Kid Leaders will help facilitate |
| Music performance | Austin Lara,Gerardo Perez,School Admin,Students | 12/14/22 | Instruments | Students perform for Toy Drive event | Woodcraft Rangers – Music will group will host event |
| Budget |
| Total budget | Instrument storage | Music equipment | Event budget |
| $1000 | $500 | $300 | $200 |